## HandoverPlan
HandoverPlan - WOW
| Update Date |  | 2017-06-28
| Project |  | WOW Project | https://docs.google.com/a/glv.co.jp/spreadsheets/d/1j64dCzYRLqJbCo_VkSyLpyRdaNJMGeil32rczCY4lZQ/edit?usp=drive_web
[5 empty] | Detail Document | [6 empty] | Handover MTG
No | System |  | From Person | To Person | Man Hour | Start Date (Est) | End Date (Est) | Start Date (Act) | End Date (Act) | Action | Document | Man Hour | Start Date (Est) | End Date (Est) | Start Date (Act) | End Date (Act) | MTG Document | State
| WOW Navigator | [10 empty] | 1
|  | Login screen | PhươngNV | Inaba | 2 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | Update | https://docs.google.com/spreadsheets/d/1On79R8Jt3WIAMZj65CWEGkWl7uT0FE4Usi8Mdw3JOlA/edit#gid=724894565 |  | 2017-11-08 | 2017-11-08 |  |  |  | Done
|  | My page | PhươngNV | Inaba | 2 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | Update | https://docs.google.com/spreadsheets/d/1On79R8Jt3WIAMZj65CWEGkWl7uT0FE4Usi8Mdw3JOlA/edit#gid=1559974571 |  | 2017-11-08 | 2017-11-08 |  |  |  | Done
|  | Message-box | PhươngNV | Inaba | 2 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | Update | https://docs.google.com/spreadsheets/d/1On79R8Jt3WIAMZj65CWEGkWl7uT0FE4Usi8Mdw3JOlA/edit#gid=464254572 |  | 2017-11-08 | 2017-11-08 |  |  |  | Done
|  | Vehicle detailed information | PhươngNV | Inaba | 2 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | Update | https://docs.google.com/spreadsheets/d/1On79R8Jt3WIAMZj65CWEGkWl7uT0FE4Usi8Mdw3JOlA/edit#gid=737823861 |  | 2017-11-08 | 2017-11-08 |  |  |  | Done
|  | Vehicle comparison | PhươngNV | Inaba | 2 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | Update | https://docs.google.com/spreadsheets/d/1On79R8Jt3WIAMZj65CWEGkWl7uT0FE4Usi8Mdw3JOlA/edit#gid=841916437 |  | 2017-11-08 | 2017-11-08 |  |  |  | Done
|  | Stock search | PhươngNV | Inaba | 2 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | Update | https://docs.google.com/spreadsheets/d/1On79R8Jt3WIAMZj65CWEGkWl7uT0FE4Usi8Mdw3JOlA/edit#gid=1769880401 |  | 2017-11-08 | 2017-11-08 |  |  |  | Done
|  | Campaign information | PhươngNV | Inaba | 2 | 2017-06-29 | 2017-06-29 | 2017-06-29 | 2017-06-29 | Update | https://docs.google.com/spreadsheets/d/1On79R8Jt3WIAMZj65CWEGkWl7uT0FE4Usi8Mdw3JOlA/edit#gid=1151914510 |  | 2017-11-08 | 2017-11-08 |  |  |  | Done
|  | Store blog | PhươngNV | Inaba | 2 | 2017-06-29 | 2017-06-29 | 2017-06-29 | 2017-06-29 | Update | https://docs.google.com/spreadsheets/d/1On79R8Jt3WIAMZj65CWEGkWl7uT0FE4Usi8Mdw3JOlA/edit#gid=1151914510 |  | 2017-11-08 | 2017-11-08 |  |  |  | Done
| WOW Manager | [16 empty] | Done
|  | Login screen | PhươngNV | Inaba | 2 | 2017-06-29 | 2017-06-29 | 2017-06-30 | 2017-06-30 | Update | https://docs.google.com/spreadsheets/d/1_0Ers_3Bz1BHe3J6VWE4z3F5dr3yRhYAyRp0OeNaXqM/edit#gid=1742005220 | 1 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 |  | Done
|  | Header | PhươngNV | Inaba | 2 | 2017-06-29 | 2017-06-29 | 2017-06-30 | 2017-07-07 | Update | https://docs.google.com/spreadsheets/d/1_0Ers_3Bz1BHe3J6VWE4z3F5dr3yRhYAyRp0OeNaXqM/edit#gid=1198468506 |  | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 |  | Done
|  | Reception management | PhươngNV | Inaba | 24 | 2017-06-30 | 2017-07-04 |  |  | CreateNew | https://docs.google.com/spreadsheets/d/1_0Ers_3Bz1BHe3J6VWE4z3F5dr3yRhYAyRp0OeNaXqM/edit#gid=1715639029 |  | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 |  | Done
|  | Behavior management | PhươngNV | Inaba | 24 | 2017-07-04 | 2017-07-06 |  |  | CreateNew | https://docs.google.com/spreadsheets/d/1_0Ers_3Bz1BHe3J6VWE4z3F5dr3yRhYAyRp0OeNaXqM/edit#gid=1715639029 |  | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 |  | Done
|  | Vehicle management | PhươngNV | Inaba | 24 | 2017-07-06 | 2017-07-11 |  |  | CreateNew | https://docs.google.com/spreadsheets/d/1_0Ers_3Bz1BHe3J6VWE4z3F5dr3yRhYAyRp0OeNaXqM/edit#gid=1191955428 |  | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 |  | Done
|  | Numerical management | PhươngNV | Inaba | 2 | 2017-07-11 | 2017-07-11 |  |  | Update | https://docs.google.com/spreadsheets/d/1_0Ers_3Bz1BHe3J6VWE4z3F5dr3yRhYAyRp0OeNaXqM/edit#gid=34334893 |  | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 |  | Done
|  | Message-box | PhươngNV | Inaba | 2 | 2017-07-11 | 2017-07-11 |  |  | Update | https://docs.google.com/spreadsheets/d/1_0Ers_3Bz1BHe3J6VWE4z3F5dr3yRhYAyRp0OeNaXqM/edit#gid=34334893 |  | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 |  | Done
| WOW API | [16 empty] | Done
|  | API Document | PhươngNV | Inaba | 2 | 2017-07-11 | 2017-07-11 |  |  | Update | https://docs.google.com/spreadsheets/d/12ftBsEgT9DlCaUGy9aICIziRex5O3xLzkrTt2qhibwo/edit#gid=1806490149 | 2 | 2017-11-10 | 2017-11-10 |  |  |  | Done
WOW Database
|  | ER diagram | PhươngNV | Inaba | 2 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | Update | https://docs.google.com/spreadsheets/d/1KKfaygOtj3QsyFV2dxcD4g9j_z3y0XqhoadP3VL_BXQ/edit#gid=1536192089 | 1 | 2017-11-13 | 2017-11-13 | 2017-11-13 | 2017-11-13 |  | Done
|  | List table structure | PhươngNV | Inaba | 2 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | Update | https://docs.google.com/spreadsheets/d/1KKfaygOtj3QsyFV2dxcD4g9j_z3y0XqhoadP3VL_BXQ/edit#gid=308879468 |  | 2017-11-13 | 2017-11-13 | 2017-11-13 | 2017-11-13 |  | Done
WOW Maintenance
|  | Update staff data | PhươngNV | Inaba | 2 |  |  |  |  | Update | https://docs.google.com/spreadsheets/d/1MvYfYI8C9XAw3hJQ_jm7Vfb8_mTd2VSpSH4x7DueeIw/edit#gid=1261869834 https://gulliver.backlog.jp/wiki/S_GWS/Home#__wiki_header_20 | 1 | 2017-11-14 | 2017-11-14 | 2017-11-13 | 2017-11-13 |  | Done
|  | Export data monthy | PhươngNV | Inaba | 2 |  |  |  |  | Update | https://docs.google.com/spreadsheets/d/1wpvRaX6c47AwHVlOrYc7GBUSHT6JM_Bn6RBLxMZGmyg/edit#gid=1261869834 | 1 | 2017-11-14 | 2017-11-13 | 2017-11-13 | 2017-11-13 |  | Done
|  | Recovery deleted car | PhuongNV | Inaba | [6 empty] | https://docs.google.com/spreadsheets/d/1hlkknsVqWNC5prybt1LeIzA0V7y7-IaRgqFJcEhbSEc/edit#gid=1666549119 | [6 empty] | Done
| 新WOW環境設定 |  | PhuongNV | Inaba | [7 empty] | 2 | 2017-11-15 | 2017-11-15 |  |  | Inabaさん：đã settup xong Quang: đã setup được Wow-manager! (Quang chưa có account nên ko lấy được source)
| 旧Wow-Api |  | PhươngNV | Inaba | [5 empty] | Update |  | 2 | 2017-11-16 | 2017-11-16 |  |  |  | Done
| 旧Wow-Manager |  | PhươngNV | Inaba | [5 empty] | Update |  |  | 2017-11-16 | 2017-11-16 |  |  |  | Done
| 旧Wow-Navigator |  | PhươngNV | Inaba | [5 empty] | Update |  |  | 2017-11-16 | 2017-11-16 |  |  |  | Done
| 旧Wow-Service |  | PhươngNV | Inaba | [5 empty] | Update |  |  | 2017-11-16 | 2017-11-16 |  |  |  | Done
| 旧WOW環境設定 |  | PhươngNV | Inaba | [7 empty] | 3 | 2017-11-17 | 2017-11-17 |  |  | Setup trên môi trường Dev | Done
| WOW!Factory メンテナンス |  | PhươngNV | Inaba | [6 empty] | https://gulliver.backlog.jp/wiki/S_GWS/WOW+Factory%E3%83%A1%E3%83%B3%E3%83%86%E3%82%AC%E3%82%A4%E3%83%89%E3%83%A9%E3%82%A4%E3%83%B3 | 1 | 2017-11-18 | 2017-11-18 |  |  |  | Done

## Enviroment Info
No | システム | 項目 | 開発環境 | UAT環境 | 本番環境
1 | 新Wow!Manager -source: https://gulliver.backlog.jp/git/S_GWS/WOWRenewal_Manager.git -infra: https://cacoo.com/diagrams/fOmRbWdc4Ozae820#DD109 | S3 | tran.dev-wow.jp01.ap-ne1 | tran.dev-wow.jp01.ap-ne1 | tran.wow.jp01.ap-ne1 tran.gws.jp01.ap-ne1
|  | Master Server's Ip | 54.65.107.81 | 54.65.107.81 | 172.24.214.41 (sv-jp-ex-wb06)
|  | DB | https://goo.gl/Bvfs8r (No1) | https://goo.gl/Bvfs8r (No1) | https://goo.gl/Bvfs8r (No1)
|  | Source folder | /app/ex-web/WOWRenewal_Manager/
|  | URL | https://wow-renewal-dev.cloud.glv.co.jp/ex-web/ | https://wow-renewal-dev.cloud.glv.co.jp/uat-ex-web/ | https://wow-manager.cloud.glv.co.jp/wow-manager/
2 | 新Wow!Navigator -source: https://gitlab.rzm.co.jp/wowtown/wow-navigator.git -infra: https://cacoo.com/diagrams/fOmRbWdc4Ozae820#314CD | S3 | dev.pic.devjp03.ap-ne1 | dev.pic.devjp03.ap-ne1 | tran.wow.jp01.ap-ne1
|  | Master Server's Ip | 54.65.107.81 | 54.65.107.81 | 172.24.216.153(sv-jp-ex-wb05)
|  | DB | https://goo.gl/Bvfs8r (No2) | https://goo.gl/Bvfs8r (No2) | https://goo.gl/Bvfs8r (No2)
|  | Source folder | /app/wow-navigator/wow-navigator/
|  | URL | https://wow-renewal-dev.cloud.glv.co.jp/wow-navigator/ | https://wow-renewal-dev.cloud.glv.co.jp/uat-wow-navigator/ | https://wow-signage.cloud.glv.co.jp/wow-navigator/
3 | 新Wow!Sinage-api -source: https://gitlab.rzm.co.jp/wowtown/api.git -infra: https://cacoo.com/diagrams/fOmRbWdc4Ozae820#DD109 | Master Server's Ip | 54.65.107.81 |  | 172.24.214.41 (sv-jp-ex-wb06)
|  | DB | https://goo.gl/Bvfs8r (No3) |  | https://goo.gl/Bvfs8r (No3)
|  | Source folder | app/signage-api/api/
|  | URL | https://wow-renewal-dev.cloud.glv.co.jp/signage-api/ |  | https://wow-api.cloud.glv.co.jp/signage-api/
4 | 新Wow!Wow-api -source: https://gulliver.backlog.jp/git/S_GWS/WOWRenewal_WowApi.git -infra: https://cacoo.com/diagrams/fOmRbWdc4Ozae820#DD109 | Master Server's Ip | 54.65.107.81 |  | 172.24.214.41 (sv-jp-ex-wb06)
|  | DB | https://goo.gl/Bvfs8r (No4) |  | https://goo.gl/Bvfs8r (No4)
|  | Source folder | /app/wow-api/WOWRenewal_WowApi/
|  | URL | https://wow-renewal-dev.cloud.glv.co.jp/wow-api/ |  | https://wow-api.cloud.glv.co.jp/wow-api/
5 | 旧Wow!Manager -source: https://54.248.254.200/svn/terras/Gulliver/GWS/GWS-Renew/03_Source/trunk/GWS-EX-WEB-renew -infra: https://cacoo.com/diagrams/fOmRbWdc4Ozae820#DD109 | Master Server's Ip | 172.24.160.107 |  | 172.24.213.121 (sv-jp-ex-wb01)
|  | DB | https://goo.gl/Bvfs8r (No5) |  | https://goo.gl/Bvfs8r (No5)
|  | URL | http://172.24.160.107/ex-web/ |  | https://wow-mgmt.cloud.glv.co.jp/ex-web/
6 | 旧Wow!Navigator -source: https://54.248.254.200/svn/terras/Gulliver/GWS/GWS-Renew/03_Source/trunk/GWS-WOW-Navigator-renew -infra: https://cacoo.com/diagrams/fOmRbWdc4Ozae820#D3FC4 | Master Server's Ip | 172.24.160.107 |  | 172.24.213.121 (sv-jp-ex-wb01)
|  | DB | https://goo.gl/Bvfs8r (No6) |  | https://goo.gl/Bvfs8r (No6)
|  | URL | http://172.24.160.107/wow-navigator/ |  | https://wow-navi.cloud.glv.co.jp/wow-navigator/
7 | 旧Wow!ex-api -source: https://54.248.254.200/svn/terras/Gulliver/GWS/GWS-Renew/03_Source/trunk/GWS-WOW-renew -infra: https://cacoo.com/diagrams/fOmRbWdc4Ozae820#D3FC4 | Master Sever's Ip | 172.24.160.107 |  | 172.24.213.121 (sv-jp-ex-wb01)
|  | DB | https://goo.gl/Bvfs8r (No7) |  | https://goo.gl/Bvfs8r (No7)
|  | URL | http://172.24.160.107/wow/ |  | https://gws-ex.cloud.glv.co.jp/wow-api/
8 | 旧Wow!Ss-api -source: https://54.248.254.200/svn/terras/Gulliver/GWS/GWS-Renew/03_Source/trunk/GWS-SS-renew -infra: https://cacoo.com/diagrams/fOmRbWdc4Ozae820#D3FC4 | Master Server's Ip | 172.24.160.107 |  | 172.24.213.121 (sv-jp-ex-wb01)
|  | DB | https://goo.gl/Bvfs8r (No8) |  | https://goo.gl/Bvfs8r (No8)
|  | URL | 172.24.160.107/gws-ss-renew/ |  | https://ss-ex.cloud.glv.co.jp/ss-api/
9 | 旧Wow!Service -source: https://54.248.254.200/svn/terras/Gulliver/GWS/GWS-Renew/03_Source/trunk/GWS-Service-Renew -infra: https://cacoo.com/diagrams/fOmRbWdc4Ozae820#CA2C8 | Master Server's Ip | 172.24.160.107 |  | 172.24.213.251 (sv-jp-ex-wb03)
|  | DB | https://goo.gl/Bvfs8r (No9) |  | https://goo.gl/Bvfs8r (No9)
|  | URL | 172.24.160.107/wow-app/ |  | https://app.wowtown.jp/

## DB接続
|  | 本番環境 |  |  |  | 開発環境
No | システム | インスタンス | RDS | Database | User | インスタンス | RDS | Database | User
1 | Wow-Manager | sv-jp-ex-wb06 | rds-jp-car02 | dbGwsSs | ap_gws-ss | 54.65.107.81 | rds-jp-gws-dev02.chd6sqbfd7y5.ap-northeast-1.rds.amazonaws.com | dbGwsSsDev | mnt_seta01
|  |  | rds-jp-car02 | dbGwsWow | ap_gws-wow |  | rds-jp-gws-dev02.chd6sqbfd7y5.ap-northeast-1.rds.amazonaws.com | DEV_GWS_WOWdb | mnt_seta01
|  |  | rds-jp-crm01 | dbGwsCk | ap_gws-ck |  | rds-jp-gws-dev02.chd6sqbfd7y5.ap-northeast-1.rds.amazonaws.com | dbGwsCkDev | mnt_seta01
|  |  | rds-jp-mst01 | dbGwsMaster | ap_gws-master |  | rds-jp-gws-dev02.chd6sqbfd7y5.ap-northeast-1.rds.amazonaws.com | dbGwsMaster | mnt_seta01
|  |  | rds-jp-car01-rr01c | dbGwsBs | ap_gws-bs |  | rds-jp-gws-dev02.chd6sqbfd7y5.ap-northeast-1.rds.amazonaws.com | GWS_BSdb_Renew | mnt_seta01
|  |  | rds-jp-car02 | dbGwsSinage | ap_wow-api |  | rds-jp-gws-dev02.chd6sqbfd7y5.ap-northeast-1.rds.amazonaws.com | dbwowsignage | mnt_seta01
|  |  | rds-jp-crm01 | dbGwsSf | ap_gws-sf |  | rds-jp-gws-dev02.chd6sqbfd7y5.ap-northeast-1.rds.amazonaws.com | dbGwsSfDev | mnt_seta01
2 | Wow-Navigator | sv-jp-ex-wb05 | rds-jp-car02 | dbGwsSs | ap_gws-ss | 54.65.107.81 | rds-jp-gws-dev02.chd6sqbfd7y5.ap-northeast-1.rds.amazonaws.com | dbGwsSsDev | mnt_seta01
|  |  | rds-jp-car02 | dbGwsWow | ap_gws-wow |  | rds-jp-gws-dev02.chd6sqbfd7y5.ap-northeast-1.rds.amazonaws.com | DEV_GWS_WOWdb | mnt_seta01
|  |  | rds-jp-crm01 | dbGwsCk | ap_gws-ck |  | rds-jp-gws-dev02.chd6sqbfd7y5.ap-northeast-1.rds.amazonaws.com | dbGwsCkDev | mnt_seta01
|  |  | rds-jp-mst01 | dbGwsSinage | ap_gws-sf |  | rds-jp-gws-dev02.chd6sqbfd7y5.ap-northeast-1.rds.amazonaws.com | dbwowsignage | mnt_seta01
3 | Wow-Signage-api | sv-jp-ex-wb06 | rds-jp-car02 | dbGwsSs | ap_gws-ss | 54.65.107.81 | rds-jp-gws-dev02.chd6sqbfd7y5.ap-northeast-1.rds.amazonaws.com | dbGwsSsDev | mnt_seta01
|  |  | rds-jp-car02 | dbGwsWow | ap_gws-wow |  | rds-jp-gws-dev02.chd6sqbfd7y5.ap-northeast-1.rds.amazonaws.com | DEV_GWS_WOWdb | mnt_seta01
|  |  | rds-jp-crm01 | dbGwsSinage | ap_gws-ck |  | rds-jp-gws-dev02.chd6sqbfd7y5.ap-northeast-1.rds.amazonaws.com | dbwowsignage | mnt_seta01
4 | Wow-api | sv-jp-ex-wb06 | rds-jp-car02 | dbGwsSs | ap_gws-ss | 54.65.107.81 | rds-jp-gws-dev02.chd6sqbfd7y5.ap-northeast-1.rds.amazonaws.com | dbGwsSsDev | mnt_seta01
|  |  | rds-jp-car02 | dbGwsWow | ap_gws-wow |  | rds-jp-gws-dev02.chd6sqbfd7y5.ap-northeast-1.rds.amazonaws.com | DEV_GWS_WOWdb | mnt_seta01
|  |  | rds-jp-crm01 | dbGwsMaster | ap_gws-ck |  | rds-jp-gws-dev02.chd6sqbfd7y5.ap-northeast-1.rds.amazonaws.com | dbGwsMaster | mnt_seta01
|  |  | rds-jp-crm01 | dbGwsCk | ap_gws-ck |  | rds-jp-gws-dev02.chd6sqbfd7y5.ap-northeast-1.rds.amazonaws.com | dbGwsCkDev | mnt_seta01
5 | 旧Wow-Manager | sv-jp-ex-wb06 | rds-jp-car02 | dbGwsSs | ap_gws-ss | 54.65.107.81 | rds-jp-gws-dev01.c2f80ghboscg.ap-northeast-1.rds.amazonaws.com | dbGwsSsDev | mnt_seta01
|  |  | rds-jp-car02 | dbGwsWow | ap_gws-wow |  | rds-jp-gws-dev01.c2f80ghboscg.ap-northeast-1.rds.amazonaws.com | DEV_GWS_WOWdb | mnt_seta01
|  |  | rds-jp-crm01 | dbGwsCk | ap_gws-ck |  | rds-jp-gws-dev01.c2f80ghboscg.ap-northeast-1.rds.amazonaws.com | dbGwsCkDev | mnt_seta01
|  |  | rds-jp-mst01 | dbGwsMaster | ap_gws-master |  | rds-jp-gws-dev01.c2f80ghboscg.ap-northeast-1.rds.amazonaws.com | dbGwsMaster | mnt_seta01
|  |  | rds-jp-car01-rr01c | dbGwsBs | ap_gws-bs |  | rds-jp-gws-dev01.c2f80ghboscg.ap-northeast-1.rds.amazonaws.com | GWS_BSdb_Renew | mnt_seta01
|  |  | rds-jp-crm01 | dbGwsSf | ap_gws-sf |  | rds-jp-gws-dev01.c2f80ghboscg.ap-northeast-1.rds.amazonaws.com | dbGwsSfDev | mnt_seta01